## Sheet1
Stage | Task | Owner | Status | Next Step
Requirement Gathering | Identify stakeholders | BI Lead | Pending | Conduct requirement workshops
Requirement Gathering | Conduct requirement workshops | Analyst | Pending | Document analytics needs
Requirement Gathering | Document business analytics needs | BI Lead | Pending | Validate scope
Requirement Gathering | Validate scope with stakeholders | Stakeholders | Pending | Move to Data Sourcing
Data Sourcing & STTM/Script Development | Identify data sources | Analyst | Pending | Gather metadata
Data Sourcing & STTM/Script Development | Gather metadata | Analyst | Pending | Document horizon
Data Sourcing & STTM/Script Development | Document time/volume horizon | BI Lead | Pending | Build STTM
Data Sourcing & STTM/Script Development | Build STTM and scripts | Analyst | Pending | Standardize attributes
Standardization & Alignment | Align attributes across channels | Channel Leads | Pending | Standardize naming conventions
Standardization & Alignment | Standardize naming conventions | Channel Leads | Pending | Validate recon reports
Standardization & Alignment | Validate recon reports | Channel Leads | Pending | Move to Data Engineering
Data Engineering & Data Quality | Deploy scripts to PROD/Sandbox | Data Engineer | Pending | Perform data quality validation
Data Engineering & Data Quality | Perform data quality validation | Data Engineer | Pending | Write to BI Datamart
Data Engineering & Data Quality | Write validated tables to BI Datamart | Data Engineer | Pending | Create Semantic Models
Semantic Model Creation | Build Semantic Models in Cortex Analyst | Cortex Analyst | Pending | Align with glossary
Semantic Model Creation | Align with glossary and job aids | Cortex Analyst | Pending | Document semantic layers
Semantic Model Creation | Document semantic layers | Cortex Analyst | Pending | Train semantic models
Semantic Model Training | Train with custom instructions | Cortex Analyst | Pending | Map logical views
Semantic Model Training | Map logical views | Cortex Analyst | Pending | Validate with queries
Semantic Model Training | Validate with tested queries | Cortex Analyst | Pending | Ensure attribute management
Semantic Model Training | Ensure attribute management | Cortex Analyst | Pending | Move to Integration
Integration with Snowflake Intelligence | Add Analyst to Snowflake Agent | BI Lead | Pending | Deploy Agent
Integration with Snowflake Intelligence | Deploy Agent into Snowflake Intelligence | BI Lead | Pending | Demo to stakeholders
Integration with Snowflake Intelligence | Demo to stakeholders | BI Lead | Pending | Onboard stakeholders
Stakeholder Onboarding | Conduct end-user training | Trainer | Pending | Provide documentation
Stakeholder Onboarding | Provide documentation | BI Lead | Pending | Gather feedback
Stakeholder Onboarding | Gather feedback | Stakeholders | Pending | Move to Monitoring
Monitoring & CI/CD Loop | Set up monitoring | BI Lead | Pending | Automate CI/CD
Monitoring & CI/CD Loop | Automate CI/CD | DevOps | Pending | Continuous feedback
Monitoring & CI/CD Loop | Incorporate continuous feedback | BI Lead | Pending | Close loop